## Slide 1
PYTHIA
6-Week Delivery Plan

## Slide 2
DELIVERY TIMELINE & MODEL EVALUATION
6-Week Sprint Milestones
01
Foundation & Infrastructure
Week 1-2
Data ingestion pipeline with multi-tenant isolation
PostgreSQL + Redis feature store, FastAPI microservice + CI/CD
Deliverable: Working data pipeline, API with health checks
02
AI Models & Integration
Week 3-4
Azure OpenAI integration, Anomaly detection (Isolation Forest), Churn prediction (XGBoost)
Prompt versioning system + Model evaluation framework
Deliverable: 3 production-ready models with safety filters
03
Testing & Optimization
Week 5
Load testing, caching (60%+ hit rate), unit tests (80% coverage)
Grafana dashboards, cost optimization
Deliverable: Performance benchmarks (p95 < 500ms), cost analysis
04
Production Deployment
Week 6
Canary deployment, security audit, documentation, incident playbooks
Deliverable: Production launch with zero P1 incidents
Time Allocation: 70% Delivery | 20% Experimentation | 10% Technical Debt

## Slide 3
Model Evaluation Approach
LLM Summarization
Automated: ROUGE scores, semantic similarity, toxicity detection
Human: Weekly 50-sample review (relevance, accuracy, actionability)
Target: User satisfaction > 4.0/5, hallucination < 2%
Anomaly Detection
Metrics: Precision > 0.75, Recall > 0.70, F1 > 0.72
Validation: Labeled dataset, 30-day rolling evaluation
Target: False positive < 5%, latency < 200ms
Predictive Models
Metrics: ROC-AUC > 0.80, Precision@10% > 0.60
Testing: 20% holdout, temporal validation
Target: Measured business impact ($)
Production Gate Criteria
✓ Accuracy within 5% of baseline | ✓ p95 latency < 500ms | ✓ No tenant data leakage | ✓ 100% toxicity filter | ✓ Cost < $0.05/insight
Continuous Monitoring: Daily (errors, distributions) | Weekly (drift, cost) | Monthly (retraining, bias audits)

## Slide 4
COMMUNICATION & INCIDENT MANAGEMENT
Team Communication Plan
Squad Structure (3 Engineers)
ML Engineer
Model development, prompt engineering, evaluation
Data Engineer
Pipelines, ETL, feature store, data quality
MLOps Engineer
CI/CD, infrastructure, monitoring, incidents

## Slide 5
Communication Rhythm
Daily (Async - 15 min)
Slack standup by 10 AM (progress, blockers)
Monday (1 hour)
Sprint planning with dependencies identified
Wednesday (45 min)
Model review (metrics, failures, optimization)
Friday (30 min)
Cross-team sync with backend/frontend + weekly leadership email
Documentation: Notion (ADRs, model cards, runbooks) | Code (READMEs, docstrings, Swagger)

## Slide 6
Incident Handling & Fallback Logic
Fallback Architecture (Cascade)
Primary
Azure OpenAI
Fallback 1
Anthropic Claude
Fallback 2
Cached Insights
Fallback 3
Rule-Based Analysis
Always return response with quality metadata. Never 500 errors to users.
Common Incidents & Response
Incident
Severity
Detection
Fallback Strategy
SLA
LLM API Outage
P1
503/429 errors, latency > 30s
Auto-switch to Claude → Cache → Rules
Immediate
Model Drift
P2
Accuracy drops > 10% (3 days)
Rollback to v-1, schedule retraining
< 1 hour
High Latency
P2
p95 > 2s
Scale K8s pods, emergency cache mode
< 30 min
Data Pipeline Fail
P3
No data in 2 hours
Serve stale data with timestamp warning
< 2 hours
Hallucinations
P2
User reports, safety flags
Disable prompt, use conservative template
Immediate
On-Call: 7-day rotations, PagerDuty alerts | Escalation: P1 → Manager immediately | Unresolved 1hr → Senior engineer | 4hr → Director
Postmortem: Required for P1/P2 within 48 hours (blameless, timeline, root cause, action items)

## Slide 7
SUCCESS METRICS & RISK MITIGATION
Engineering Health Metrics
Model Performance
Model drift rate: < 5%/month
Prediction accuracy: > 85%
Hallucination rate: < 2%
Operational Excellence
Latency p95: < 500ms
Uptime: > 99.5%
Error rate: < 1%
Cache hit rate: > 60%
Cost Efficiency
Cost per insight: < $0.05
Monthly LLM budget: < $5,000
Savings via caching: ~40%
Development Velocity
Deploy frequency: 2x/week
Test coverage: > 80%
Deployment success: > 95%

## Slide 8
Week 6 Success Criteria
Technical Milestones
✓ 3 models in production
✓ p95 < 500ms
✓ Error rate < 1%
✓ Test coverage > 80%
✓ Zero critical vulnerabilities
Business Outcomes
✓ 10,000 insights/day
✓ Cost < $0.05/insight
✓ User satisfaction > 4.0/5
✓ Zero P1 incidents
✓ Documentation complete

## Slide 9
Top 5 Risks & Mitigation
1
LLM costs exceed budget
Aggressive caching (60%+), batch processing, model tiering (GPT-3.5 for simple tasks)
2
Model accuracy insufficient
Define minimum viable accuracy Week 2, ship & iterate post-launch
3
Integration delays
Weekly backend/frontend syncs, API contract locked Week 1, mock endpoints ready
4
Data quality issues
Validation pipeline, quality dashboards, automated alerts on anomalies
5
Scaling under production load
Load testing Week 5, Kubernetes auto-scaling, fallback modes configured

## Slide 10
Key Technologies
FastAPI, PostgreSQL+pgvector, Redis, Azure OpenAI, Kubernetes, Prometheus/Grafana
Contact
#ai-team (Slack)
Notion docs
PagerDuty on-call
Weekly Friday updates to leadership